Event Schedule Planner 2015

|  |  |
| --- | --- |
|  |  |
| |  |  | | --- | --- | | Project/Event | Cookies & Queens Royal Tea Party | | Organizer | Brandi King 530-227-5484 | | This is a fundraiser to buy toys for the Shasta Lake Children’s Christmas Party. Event is for all ages, the goal is to raise $3000. |
|  |  |

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| |  |  |  | | --- | --- | --- | | Project Phase | Starting | Ending | | Phase 1 Volunteer Sign-ups | 5.27.2015 | 6.23.2015 | | Phase 2 Advertising | 6.24.2015 | 7.21.2015 | | Phase 3 Castle Design | 7.22.2015 | 8.4.2015 | | Phase 4 Games/Craft | 8.5.2015 | 8.18.2015 | | Phase 5 Menu / mUSIC | 8.19.2015 | 8.25.2015 | | Phase 6 rsvp/Ticket Sales | 8.26.2015 | 9.23.2015 | | PHASE 7 Tea Ettiquette | 9.16.2015 | 9.16.2015 | | |  |  |  | | --- | --- | --- | | Project Phase | Starting | Ending | | Phase 8 Tea Party Set Up | 9.25.2015 | 9.25.2015 | | Phase 9 Tea Party | 9.26.2015 | 9.27.2015 | | Phase 10 Clean up | 9.27.2015 | 9.27.2015 | |  | [Select Date] | [Select Date] | |  | [Select Date] | [Select Date] | |  | [Select Date] | [Select Date] | |  | [Select Date] | [Select Date] | |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| May | June | July | August | September | October |
| |  |  |  |  |  |  |  | | --- | --- | --- | --- | --- | --- | --- | | M | T | W | T | F | S | S | |  |  |  |  | 1 | 2 | 3 | | 4 | 5 | 6 | 7 | 8 | 9 | 10 | | 11 | 12 | 13 | 14 | 15 | 16 | 17 | | 18 | 19 | 20 | 21 | 22 | 23 | 24 | | 25 | 26 | 27 | 28 | 29 | 30 | 31 | |  |  |  |  |  |  |  | | |  |  |  |  |  |  |  | | --- | --- | --- | --- | --- | --- | --- | | M | T | W | T | F | S | S | | 1 | 2 | 3 | 4 | 5 | 6 | 7 | | 8 | 9 | 10 | 11 | 12 | 13 | 14 | | 15 | 16 | 17 | 18 | 19 | 20 | 21 | | 22 | 23 | 24 | 25 | 26 | 27 | 28 | | 29 | 30 |  |  |  |  |  | |  |  |  |  |  |  |  | | |  |  |  |  |  |  |  | | --- | --- | --- | --- | --- | --- | --- | | M | T | W | T | F | S | S | |  |  | 1 | 2 | 3 | 4 | 5 | | 6 | 7 | 8 | 9 | 10 | 11 | 12 | | 13 | 14 | 15 | 16 | 17 | 18 | 19 | | 20 | 21 | 22 | 23 | 24 | 25 | 26 | | 27 | 28 | 29 | 30 | 31 |  |  | |  |  |  |  |  |  |  | | |  |  |  |  |  |  |  | | --- | --- | --- | --- | --- | --- | --- | | M | T | W | T | F | S | S | |  |  |  |  |  | 1 | 2 | | 3 | 4 | 5 | 6 | 7 | 8 | 9 | | 10 | 11 | 12 | 13 | 14 | 15 | 16 | | 17 | 18 | 19 | 20 | 21 | 22 | 23 | | 24 | 25 | 26 | 27 | 28 | 29 | 30 | | 31 |  |  |  |  |  |  | | |  |  |  |  |  |  |  | | --- | --- | --- | --- | --- | --- | --- | | M | T | W | T | F | S | S | |  | 1 | 2 | 3 | 4 | 5 | 6 | | 7 | 8 | 9 | 10 | 11 | 12 | 13 | | 14 | 15 | 16 | 17 | 18 | 19 | 20 | | 21 | 22 | 23 | 24 | 25 | 26 | 27 | | 28 | 29 | 30 |  |  |  |  | |  |  |  |  |  |  |  | | |  |  |  |  |  |  |  | | --- | --- | --- | --- | --- | --- | --- | | M | T | W | T | F | S | S | |  |  |  | 1 | 2 | 3 | 4 | | 5 | 6 | 7 | 8 | 9 | 10 | 11 | | 12 | 13 | 14 | 15 | 16 | 17 | 18 | | 19 | 20 | 21 | 22 | 23 | 24 | 25 | | 26 | 27 | 28 | 29 | 30 | 31 |  | |  |  |  |  |  |  |  | |